## Yearly Plan
Month | Project Setup | CI | CD | Backend | Frontend
January | Setup Github Repository
February | Setup Project Scaffolding | Setup Azure Cloud Shell
March | Finalize Documentation | Setup Github actions for CI |  | Analysis of the goal
April |  | Add Pytest as Testing Suite |  | API design - return no data
May |  | Test CI using Github Actions |  | API incl data
June |  |  |  | ML algo runs
July |  |  | Evaluate cloud providers | ML evaluated | Write User Stories
August |  |  | Select appropriate cloud provider - Azure | Modify the Predict Endpoint | Setup API connection
September |  |  | Setup Azure pipelines for CD | Backend documentation finalized | GUI Design
October | Complete README |  | Deploy Webapp via Cloud Shell | QA | GUI Implementation
November | Record Demo Video |  | Pipeline pushes artifacts |  | Create User manual
December |  |  | Rollback and Upgrade work |  | QA
| Goals | Goals | Goals | Goals | Goals
| 1. Version control is set up. | 1. Pipeline builds & tests code. | 1. Pipeline pushes artifacts on cloud. |  | 1. Frontend connects via API.
| 2. Setup documented for easy developer onboarding. |  | 2. Pipeline capable of updates & rollbacks. |  | 2. GUI to provide access all functions exists.
3. User manual provided.
Difficulty of Task: |  |  |  | 1. Machine Learning algorithms do the magic they're supposed to do.
Hard |  |  |  | 2. System is scalable and runs on selected cloud.
Medium |  |  |  | 3. ML system is fully documented.
Easy

## Q1 Plan
Week | Project Setup | CI | Backend
2024-01-07 | Create Trello Board
2024-01-14 | Access management concept
2024-01-21 | Setup Git Repository
2024-01-28 | Setup ssh keys
2024-02-04 | Create Project scaffolding
2024-02-11 | Onboard backend developers
2024-02-18 |  | Github Actions enabled
2024-02-25 |  | Build server with mock pipeline
2024-03-03 |  | Project builds
2024-03-10 |  |  | Development kick off
2024-03-17
2024-03-24 |  |  | Analysis - system goals
2024-03-31
| Goals | Goals
1. Project is set up
1. Initial pipeline performs stages checkout, build, test.
1. Developers onboarded
2. Analysis defines project targets and KPIs.
Difficulty of Task:
Hard
Medium
Easy

## Q2 Plan
Week | CI | Backend
2024-04-07
2024-04-14 |  | API design - no data returned
2024-04-21
2024-04-28 | Add initial tests to pipeline
2024-05-05 | Initial test passes
2024-05-12
2024-05-19 |  | API includes data
2024-05-26 | Execute Full CI pipeline
2024-06-02
2024-06-09
2024-06-16 |  | ML algorithm runs
2024-06-23
2024-06-30
| Goals | Goals
| 1. Pipeline builds & tests code. | 1. Initial ML algorithm runs locally.
Difficulty of Task:
Hard
Medium
Easy

## Q3 Plan
Week | Backend | Frontend | CD
2024-07-07
2024-07-14 |  | User stories created
2024-07-21 |  |  | Cloud providers evaluated
2024-07-28 | ML evaluated
2024-08-04 |  |  | Cloud provider selected - Azure
2024-08-11
2024-08-18 |  | Setup API connection to backend
2024-08-25 | Concept for cloud
2024-09-01
2024-09-08 |  |  | Deploy Webapp via Cloud Shell
2024-09-15 |  | GUI design implementation
2024-09-22 | Backend documentation
2024-09-29
| Goals | Goals | Goals
| 1. Backend ML algo evaluated. | 1. User stories defined. | 1. Cloud provider selected.
| 2. Backend Documentation. | 2. GUI designed. | 2. System deployed on cloud.
Difficulty of Task:
Hard
Medium
Easy

## Q4 Plan
Week | Backend | Frontend | CD
2024-10-05 | QA
2024-10-12 | QA
2024-10-19 | QA | GUI implemented | Pipeline pushes artifacts
2024-10-26 | QA
2024-11-02 | QA | User Manual - chapters defined | Rollbacks concept
2024-11-09 | QA | User Manual - Chapter 1
2024-11-16 | QA | User Manual - Chapter 2 | Rollbacks implemented
2024-11-23 | QA | User Manual - Chapter 3
2024-11-30 | QA | User Manual reviewed | Upgrades concept
2024-12-07 | QA | QA
2024-12-14 | QA | QA | Upgrades implemented
2024-12-21 |  | QA
| Goals | Goals
| 1. System thoroughly tested. | 1. GUI implemented | 1. Pipeline capable of rollbacks.
|  | 2. GUI tested. | 2. Pipeline capable of upgrades using newest artifacts.
3. User manual written.
Difficulty of Task:
Hard
Medium
Easy